## Лист1
№ | Tasks | Members | S | M | A | R | T
[7 empty] | Start Time | End Time
1 | Problem Analysis | Repnikov Alexey Savranchuk Leonard Akuov Ilyas | Market research and analyse the problems | Count of found material = 2 | At least 3 science material related to problem | Because we need to know the problems of our topic | 2020-10-05 | 2020-10-12
2 | UML model of project | Repnikov Alexey Savranchuk Leonard Akuov Ilyas | Create a model of project to understand how the system of project works | Clarity and correctness = 0% | Clarity and correctness should be at least 80% | It will help us to create our app and reduce the mistakes in the system | 2020-10-13 | 2020-11-12
3 | Building UX/UI design | Savranchuk Leonard | Create a wareframe and maket for applications |  |  |  | 2020-11-13 | 2021-01-13
4 | Building prototype of application | Repnikov Alexey Akuov Ilyas | Create a prototype based on wareframe and layout | Completeness of prototype = 0% | Completeness of prototype should be 100% | It will help us to show how app works | 2021-01-14 | 2021-02-14
5 | Database design | Akuov Ilyas | Planning a database for the back-end | Normalization = N0 | At least N3 level for each table | It will help us create correct database | 2021-02-15 | 2021-03-01
6 | Database creating | Akuov Ilyas | Creating database | Correctness with database model = 0% | Correctness of database model should be 90% | We need database to store information | 2021-03-02 | 2021-04-02
7 | Creating server for app | Repnikov Alexey | Creating back-end for app | Server stability = 0% | Stability of server should be 100% | We need server to store and organize data | 2021-04-03 | 2021-05-03
8 | Adding additional modules into app | Repnikov Alexey Akuov Ilyas | Implementation of ideas thatappeared in the development process |  |  |  | 2021-05-04 | 2021-05-14
9 | Testing and debugging | Savranchuk Leonard | Finding and removing errors |  |  |  | 2021-05-15 | 2021-05-31